## ict services operational
Risk Number | ISP Pillar | Goal | Risk Name | Due Date | Status | Risk Description | Root Cause | Consequences | Risk Category (As per the approved RAT) | Impact | Likelihood | Inherent Exposure | Inherent Rating | Control Effectiveness: How effective is the control in addressi | Residual Exposure (New) | Risk Owner | Current Controls (What mechanism do we have in place to ensure | Type of Control (Preventative/Detective) | Control Frequency | Key Risk Indicator (KRI) | Action plan to further improve the Controls and Mitigate the Ri | Action Owner | Status Update Term1 | Status Update Term2 | Status Update Term3 | Status Update Term4 | Secondary Risk Owner
1 | Future-ready graduates who make a positive societal impact | Develop and maintain a reliable, scalable IT Infrastructure that effectively supports university operations. | Extended downtime | 2025-12-26 | Unresolved | Unreliable and ailing infrastructure could results in service outages | Failure to provide preventative maintenance of backup power in the data centres, proper patch management solution and Inadequate backup frequencies. | Data loss compromised business continuity. | Learning | 2 | 3 | 6 | Medium | Satisfactory | Priority 3 | Directorate ICT SERVICES | Daily backup on Prem and on cloud. Offsite backups | Detective | Triennial |  | Backup Strategy & Management (Secure, encrypted & tested backups).Updates, Patch & Vulnerability Management (Status and Schedule)Logging | Masilo Rakgoale | Cloud backup Project at completion stage and to be approved and signed by the project steering committee. The new system Microsoft Intune is being planned to be implemented with the Vendors. | Cloud backup Project at completion stage and to be approved and signed by the project steering committee. The new system Microsoft Intune is being planned to be implemented with the Vendors. | Cloud backup Project at completion stage and to be approved and signed by the project steering committee. The new system Microsoft Intune is being planned to be implemented with the Vendors. | Cloud backup Project at completion stage and to be approved and signed by the project steering committee. The new system Microsoft Intune is being planned to be implemented with the Vendors. | DVC Operations
2 | Impactful research, innovation, engagement and technology transfer to foster growth, development and sustainability | Implement robust operational practices to ensure high availability, performance, and disaster recovery capabilities | Continuous service disruption | 2025-12-27 | Resolved | Ongoing disruptions can increase the data corruption, data access and unstable service availability | Inadequate Infrastructure Design, Monitoring of IT infrastructure without rapid response. and Vendor or Third-Party SLAs | Data loss, system instability and Failed audit and Institutional reputation and trust by stakeholders | Learning | 1 | 3 | 3 | Low | Satisfactory | Priority 3 | Directorate ICT SERVICES | Monitoring of the infrastructure, change control and vendor management SLA | Preventative | Triennial |  | Alerting &amp; Monitoring. Engage in Vendor Management and SLA Improvements. Review the current infrastructure architectures. | Masilo Rakgoale | For monitoring tools the infrastructure is in progress implemented by the monitoring supplier. | For monitoring tools the infrastructure is in progress implemented by the monitoring supplier. | For monitoring tools the infrastructure is in progress implemented by the monitoring supplier. | For monitoring tools the infrastructure is in progress implemented by the monitoring supplier.
3 | Service and operational excellence through resource optimization | Strengthen network security by implementing advanced protection measures, enhancing incident response, and enforcing compliance with security policies. | Inadequate IT Security controls | 2025-12-28 | In Progress | Staff and students not adequately trained in identifying and responding to cyber threats Exposure to malware, phishing and unauthorised access to data and systems | Insufficient cybersecurity knowledge and awareness among employees and students Inadequate Email Filtering, Web Security, Remote Access Management and system hardening | Increased data breaches, financial losses, and system disruptions due to susceptibility to phishing attacks and ransomware infections. Data breaches, malware infections, and unauthorized access. Productivity loss, compliance violations, and financial losses. Reputational damage, legal repercussions, and overall security risks. | Learning | 4 | 3 | 12 | High | Weak | Priority 1 | Directorate ICT SERVICES | Webmail and Non-compulsory training Malware will be delivered to users that will compromise systems. | Detective | Triennial |  | Implement a compulsory cybersecurity awareness program for all staff and students Deploy advance EDR and XDR tools Expand MFA coverage Implement password management tools Use AI technology to detect anomalous behaviour Implement encryption Conduct offensive and defensive attack simulations Improve SOC and SIEM capability | Sundaram Chatty | Investigating Awareness programs that will form part of cybersecurity tender requirements | Investigating Awareness programs that will form part of cybersecurity tender requirements | Investigating Awareness programs that will form part of cybersecurity tender requirements | Investigating Awareness programs that will form part of cybersecurity tender requirements
4 | Digitally-Advanced University | Establish a comprehensive IT governance and risk management framework to proactively identify, assess, and mitigate IT risks. | Cybersecurity exposure | 2025-12-29 | Unresolved | User and System access does not adopt a zero-trust methodology | Identity and Access Management does not ensure secure access and auditing | Unauthorised access Cybercrime / Cybersecurity risk and Ransomware Loss and data Ineffective Cyber Threat Response System services Unavailability CT Services and data will be compromised Unsecure systems | Technology | 3 | 4 | 12 | High | Weak | Priority 1 | Directorate ICT SERVICES | Complex passwords and Manual penetration | Detective | Triennial |  | Expand MFA coverage Implement password management tools Use AI technology to detect anomalous behaviour Implement encryption Conduct offensive and defensive attack simulations Improve SOC and SIEM capability | Sundaram Chatty |  |  |  | Penetration Scheduled of October MFA improved with country access restriction Other services are tender dependent
5 | Future-ready graduates who make a positive societal impact | Oversee the IT landscape, guiding the strategic direction, architectural decisions, and governance processes | Governance and Architectural Misalignment | 2025-12-30 | In Progress | Lack of governance and inconsistent architectural decisions | Insufficient oversight and governance frameworks in place | Strategic misalignment, reduced operational efficiency, and increased risk of regulatory non-compliance | Learning | 4 | 5 | 20 | Extreme | Satisfactory | Priority 1 | Directorate ICT SERVICES | Regular governance (ITIC) meetings, IT strategy review, enterprise architecture programme | Detective | Triennial | Number of governance (ITIC + EAB) meetings held | Establish regular governance review meetings and introduce more rigorous architectural decision-making processes. | Mafika Nkambule | Risk acknowledged, governance meetings in place | Action plan drafted, awaiting review | Scheduled for October updates
6 | Impactful research, innovation, engagement and technology transfer to foster growth, development and sustainability | Enhance IT Operational Efficiency and Governance | Operational Inefficiency | 2025-12-31 | On Track | Operational inefficiencies leading to project delays, resource wastage, and non-compliance risks | Outdated processes, inadequate metrics, and lack of clear roles | Project delays, increased operational costs, missed targets, and regulatory non-compliance | Planning | 4 | 5 | 20 | Extreme | Satisfactory | Priority 1 | Directorate ICT SERVICES | Process reviews and implementation of performance metrics, training of staff on operational governance policies | Detective | Triennial | Percentage of operational processes optimized | Automate key processes, improve resource allocation tracking, and implement updated operational metrics and KPIs | Mafika Nkambule | Risk being managed, 10% of processes reviewed | On track for completion, processes reviewed | Processes being optimized; further action required
7 | Service and operational excellence through resource optimization | Promote efficient and innovative system development and integration that aligns with the university's strategic goals. | Incomplete Business requirements | 2026-01-01 |  | Incomplete requirements from stakeholders can lead to development of systems that do not meet user needs | Incomplete stakeholder engagement and communication during the requirements-gathering process. | Incomplete requirements can result in systems that fail to meet user needs, leading to costly rework, project delays, and reduced user satisfaction. | Planning. Human Resource. | 3 | 2 | 6 | Medium | Satisfactory | Priority 3 | Directorate ICT SERVICES | Ensure early and continuous engagement with all relevant stakeholders throughout the requirements-gathering process. | Detective | Triennial |  | Implement a clear, documented process for gathering, reviewing, and validating requirements. | Obakeng Senokwane | Established a stakeholder engagement plan | Implemented a formalized requirements-gathering process with clear documentation templates | Developed and reviewed use case documentation to ensure comprehensive coverage of all system needs
8 | Digitally-Advanced University | Ensure that IT systems are scalable, interoperable, and can evolve with changing academic and administrative needs. | Rigid System Architecture | 2026-01-02 | Unresolved | Systems that are designed with inflexible architecture may not be able to adapt to future academic and administrative changes | Lack of modular design and flexibility in system architecture | Inflexible architecture can lead to difficulties in adapting to new academic or administrative requirements | Infrastructure | 4 | 4 | 16 | Extreme | Unsatisfactory | Priority 1 | Directorate ICT SERVICES | Design systems with extensibility in mind, and use modern development frameworks and APIs that support future integrations | Detective | Biannual |  | Conduct periodic reviews of the system architecture to identify potential limitations and areas for improvement | Obakeng Senokwane | Established a cross-functional architecture review team and defined the scope and schedule for periodic system reviews. | Conducted an initial assessment of existing system architecture to identify components suitable for migration to a microservices architecture. | Completed the first comprehensive review of the existing architecture, identifying key areas that limit flexibility and scalability.
9 | Future-ready graduates who make a positive societal impact | Deliver high-quality IT services that meet the university community's needs. Focus on continuous improvement through feedback, process optimisation, and adoption of best practices in service management. | Continuous improvement | 2026-01-03 | Unresolved | Lack of Proper Feedback Channels | Inadequate systems for gathering user feedback. | limited insights into areas that need improvement. | Infrastructure | 4 | 4 | 16 | Extreme | Weak | Priority 1 | Directorate ICT SERVICES | Regularly review and adjust staffing levels based on demand | Detective | Triennial |  | Use data analytics to identify areas for improvement Continuously monitor and review processes for efficiency | Joel Mampa | Automation of the Feedback form developed. | 104 responses on user satisfaction and working on analysing the report.
10 | Impactful research, innovation, engagement and technology transfer to foster growth, development and sustainability |  | User Satisfaction | 2026-01-04 | Unresolved | Misaligned with User Expectations | The services delivered may not align with the actual needs or expectations | Expectations of the university community not delivered due to insufficient stakeholder engagement. | Human Resource | 4 | 3 | 12 | High | Weak | Priority 1 | Directorate ICT SERVICES | Provide continuous training and professional development opportunities | Detective | Triennial |  | Review our IT Structure | Joel Mampa | Two (2) help desk positions filled. | The Service Desk staff is capacitated with all posts filled. Service Desk Reports using Power BI in development stage.
11 | Service and operational excellence through resource optimization |  | Service Quality | 2026-01-05 | Unresolved | Poor Vendor Performance | Third-party providers not meeting their SLAs (Service Level Agreements) | Low service quality | Human Resource, Technology | 3 | 3 | 9 | Medium | Satisfactory | Priority 3 | Directorate ICT SERVICES | Escalate and Review Breached incidents. | Detective | Yearly |  | Improved Monthly review meetings | Joel Mampa | Action out items and review SLA | Action out items and review SLA
12 | Digitally-Advanced University | Manage IT projects effectively from conception through completion, using industry-standard project management and business analysis techniques. | Addressing technical limitations and risks in technology implementation | 2026-01-06 | Unresolved | inadequate project risk assessment | insufficient understanding of project requirements, insufficient testing, lack of vendor support, inexperienced/unskilled project team with technology, resource constraints | Poor project quality output , Increased workload, | Technology | 3 | 2 | 6 | Medium | Satisfactory | Priority 3 | Directorate ICT SERVICES | Draft organisational structure, Signoffs and milestones to manage project funds | Detective | Quarterly |  | Review organisational structure | Lydia Ramothibe | ICT Draft structure was presented by Ms Lungi. | Draft was presented among ICT Exco | Draft was presented to HR for reviewal.
13 | Future-ready graduates who make a positive societal impact | Ensure projects are delivered on time, within budget, and with the desired outcomes to support strategic goals | Delivery of projects on time, within the budget | 2026-01-07 | Unresolved | Unforeseen technical issues or limitations with chosen technology | Risk of the unknown, Inefficient business continuity/ contingency management or plan. Ineffective project risk management | Stakeholder dissatisfaction, Unrealistic Timelines | Research | 1 | 2 | 2 | Housekeeping | Good | Priority 5 | Directorate ICT SERVICES | Project Coordinator, Generic project Risk register, IT Project management framework | Detective | Yearly |  | Obtaining report on Testing environment for quality assurance by Deputy director infrastructure Ensure project business continuity management | Lydia Ramothibe | Monthly review meetings are being held to obtain review reports on testing environment . | Monthly review meetings are being held. | Monthly review meetings are being held.